## Team Capacity Calculations
Team Capacity Calculations
Release Level Plan |  | Iteration Level Plan
Start | 2014-01-09 | Iteration # | # Weeks | Hours
Finish | 2014-03-27 | 1st iteration | 4 | 192
Last Day of Class | 2014-04-04 | 2nd iteration | 3 | 144
|  | 3rd iteration | 3 | 144
Work Days | 77 | 4th iteration | 1 | 48
Work Weeks | 11
# of People | 8 | Total Hours |  | 528
Hours/Week/Person | 6
Total Hours | 528

## Product Backlog
Feature Set | Description | Target Iteration
Game | create a game | 1
Game | specify game settings (# of players, player color) | 1
Game | show hotseat game board | 1
Game | peg animation | 2
Game | hotseat (offline, no AI) | 2
| simple AI | 2
Game | finish game | 2
Account | acheivements
Account | anonymous accounts
Account | edit account
Account | delete account | 3
Account | friends list
Account | game history, rank, etc.
Account | leaderboards/ranking/points based on place and # of players in the games played | 3
Account | login
Account | login with Facebook | 3
Account | logout | 3
Account | message inbox
Account | password reset through website | 3
Account | profile page
Admin | admin screen for system analytics
Admin | COPPA compliance in the EULA | 3
Game | 1st-6th place get points | 3
Game | AI takes over when user forfeit | 3
Game | determine list of players | 3
Game | demo mode (to watch AI) | 3
Game | friend request
Game | game playback
Game | in-game chat
Game | multiple games (up to 20) with notification that a game is waiting for you to make a move | 3
Game | play against an AI | 2
Game | set music/fx volume
Game | timed games (player timeout period where they forfeit after a max number of days with no activity)
Game | timeless (long) games
Game | show possible moves | 2
Game | toggle show possible moves | 3
Game | push game turn notification | 3
Help | hotseat game "help" section | 2
Web | app static webpage | 3
Network | game lobby
Game | saving 1 game | 2

## Iteration #1
Description | Estimate | Assigned | Created | Status | Completed
Communication - consolidate the requirements and design documentation | 4 | @BenStitt | 2014-01-19 | Done | 2014-02-05
Communication - create terms of service document | 2 | @BenStitt | 2014-01-19 | Done | 2014-01-29
Construction - create a board and adding pegs | 4 | Peter + @ChrisKdon | 2014-01-19 | Done | 2014-02-04
Construction - create the first 2 activities, minus the game board | 6 | @kubasub | 2014-01-19 | Done | 2014-02-04
Construction - finalize the creation of the game board grid | 8 | @ChrisKdon | 2014-01-19 | Done | 2014-02-04
Construction - UI layout files, not colours | 7 | @kubasub | 2014-01-19 | Done | 2014-02-04
Design - AI design with 4 to 5 different difficulties/strategies | 7 | @JamesKostiuk | 2014-01-19 | Done | 2014-02-04
Design - create naming conventions for Testing | 0.5 | @kubasub | 2014-01-19 | Done | 2014-01-20
Design - creating documentation of the creation of the game board grid | 4 | Peter | 2014-01-19 | Done | 2014-02-01
Design - creating documentation of the high level architecture | 10 | @ChrisKdon | 2014-01-19 | Done | 2014-02-04
Design - UI flow | 3 | @kubasub | 2014-01-19 | Done | 2014-01-20
Design - UI screen mockups with styles | 8 | @taywhited | 2014-01-19 | Done | 2014-02-02
Testing - create test plan from UI design | 4 | @SaajidM | 2014-01-19 | Done | 2014-02-04
Testing - ease of use testing | 2 | @SaajidM | 2014-02-01 | Done | 2014-02-05
Testing - implement test cases | 8 | @SaajidM | 2014-01-23 | Done | 2014-02-05
Testing - run the integration and performance tests | 2 | @SaajidM | 2014-01-19 | Done | 2014-02-05

## Iteration #1 Burndown
Date | Total | Done | To Do
2014-01-19 | 14 | 0 | 14
2014-01-20 | 14 | 2 | 12
2014-01-21 | 14 | 2 | 12
2014-01-22 | 14 | 2 | 12
2014-01-23 | 15 | 2 | 13
2014-01-24 | 15 | 2 | 13
2014-01-27 | 15 | 2 | 13
2014-01-28 | 15 | 2 | 13
2014-01-29 | 15 | 3 | 12
2014-01-30 | 15 | 3 | 12
2014-01-31 | 15 | 3 | 12
2014-02-03 | 16 | 5 | 11
2014-02-04 | 16 | 12 | 4
2014-02-05 | 16 | 16 | 0
Formulas:
Date = WORKDAY([Date, row above],1)

## Iteration #2
Description | Owner | Created | Status | Completed
#44 Use Case Saving Game | @godamnpete | 2014-02-07 | Done | 2014-02-26
UI dialog box with similar to overlay
UI mock up | @taywhited
update existing activity diagram | @kubasub
code save and load | @kubasub/@godamnpete
code UI flow control | @kubasub
Activity testing (which method are we using) | @saajid
#42 Use Case Show possible moves | @godamnpete | 2014-02-07 | Done | 2014-02-26
UI Mock up to show posssible moves | @taywhited
Code showing possible moves | @chris
activity diagrams to show the possible moves | @kubasub
UML showing the events more like a sequence diagram | @chris
Manual testing | @saajid
#43 Use Case Hotseat Game Help Section | @taywhited | 2014-02-07 | Done | 2014-02-25
UI Mockup for the help page | @taywhited
activity diagram | @kuba
UML changes to show the code design changes | @chris
Code and unit test | @kuba
Automated Activity Tests | @saajid
split into a general page class | @chris
#41 Use Case Play Against an AI | @jameskostiuk
Get AI to make a move | @jameskostiuk
create the AI interface | @chris
#61 Use Case to select AI |  | 2014-02-07 | Done | 2014-02-26
UI Mock ups | @taywhited
update game UI flow control | @kuba
code and unit testing | @kuba
Activity tests | @saajid
#40 Use Case - Finish Game | @kubasub | 2014-02-07 | Done | 2014-02-26
Checking for the win condition | @godamnpete
UI Mock ups to show who won | @taywhited |  |  |  | Needs the screen shot from @kuba
in hotseat tap button to go back to home screen or start a new game | @kubasub
#62 Testing - Create Phase 2 Plan | @saajid | 2014-02-14 | Done | 2014-02-25
#77 Create UI control tables for activities | @kubasub | 2014-02-18 | Done | 2014-02-20
#76 Create Activity UI flowchart diagrams | @kubasub | 2014-02-18 | Done | 2014-02-20
#71 Testing - Create acceptance testing criteria and verify the application passes | @saajid | 2014-02-14 | Done | 2014-02-26
#69 Testing - Gather ease of use feedback | @saajid | 2014-02-14 | Done | 2014-02-26
#68 Testing - Run tests on physical device | @saajid | 2014-02-14 | Done | 2014-02-26
#66 Testing - implement test plan SettingsActivityTest | @saajid | 2014-02-14 | Done | 2014-02-25
#65 Testing - implement test plan GameActivityTest | @saajid | 2014-02-14 | Done | 2014-02-26
#64 Testing - Implement test plan HotSeatConfigurationTest | @saajid | 2014-02-14 | Done | 2014-02-25
#67 Testing - Implement test plan FullAppIntegrationTest | @saajid | 2014-02-14 | Done | 2014-02-26
#63 Testing - Implement test plan MainActivityTest | @saajid | 2014-02-14 | Done | 2014-02-25
#58 Construction - Unit testing of Game Board | @godamnpete | 2014-02-13 | Done | 2014-02-20
Design network API | @chriskdon | 2014-02-10 | Done | 2014-02-26
#52 Create AI interface | @chriskdon | 2014-02-10 | Done | 2014-02-22
#50 Design Gamestate internals | @chriskdon | 2014-02-10 | Done | 2014-02-26
#51 Add touch detection to the Gameboard | @chriskdon | 2014-02-10 | Done | 2014-02-21
#47 Communication - create end user license agreement | @benstitt | 2014-02-10 | Done | 2014-02-25
#75 Streamlining/updating the UI flow diagram | @kubasub | 2014-02-18 | Done | 2014-02-18
#46 Construction - finalizing the gameboard grid | @godamnpete | 2014-02-07 | Done | 2014-02-13
#79 UI Mockups Collection | @taywhited | 2014-02-20 | Done | 2014-02-21
#84 Construction - Code offline game control functionality | @kubasub | 2014-02-22 | Done | 2014-02-22
#81 Add Hint Drawing | @chriskdon | 2014-02-21 | Done | 2014-02-21
#83 Construction - convert offline game mockup to xml | @kubasub | 2014-02-22 | Done | 2014-02-22
#74 Renaming HOTSEAT gameplay | @kubasub | 2014-02-16 | Done | 2014-02-22
#80 Construction - Adding a Win condition to the Grid | @godamnpete | 2014-02-21 | Done | 2014-02-21
#38 Use Case - peg animation | @taywhited | 2014-02-06 | Done | 2014-02-25
#82 Construction - code dialogs | @kubasub | 2014-02-22 | Done | 2014-02-23

## Iteration #2 Burndown
Date | Iteration 1 Total | Iteration 1 Done | Total | Done | To Do | Ideal Done
2014-02-06 | 14 | 0 | 1 | 0 | 1 | 2.1333
2014-02-07 | 14 | 0 | 7 | 0 | 7 | 4.2667
2014-02-10 | 14 | 2 | 12 | 0 | 12 | 6.4
2014-02-11 | 14 | 2 | 12 | 0 | 12 | 8.5333
2014-02-12 | 14 | 2 | 12 | 0 | 12 | 10.6667
2014-02-13 | 15 | 2 | 13 | 1 | 12 | 12.8
2014-02-14 | 15 | 2 | 22 | 1 | 21 | 14.9333
2014-02-17 | 15 | 2 | 23 | 1 | 22 | 17.0667
2014-02-18 | 15 | 2 | 26 | 2 | 24 | 19.2
2014-02-19 | 15 | 3 | 26 | 2 | 24 | 21.3333
2014-02-20 | 15 | 3 | 27 | 5 | 22 | 23.4667
2014-02-21 | 15 | 3 | 29 | 9 | 20 | 25.6
2014-02-24 | 16 | 5 | 32 | 14 | 18 | 27.7333
2014-02-25 | 16 | 12 | 32 | 21 | 11 | 29.8667
2014-02-26 | 16 | 16 | 32 | 32 | 0 | 32
Formulas:
Date = WORKDAY([Date, row above],1)

## Iteration #3
Description | Owner | Created | Status | Completed
#41 Play against an AI | @JamesKostiuk | 2014-02-07 | Done | 2014-03-18
#53 Create fancy animation code for game board | @ChrisKdon | 2014-02-07 | Done | 2014-03-05
#105 Play against medium level AI | @JamesKostiuk | 2014-02-28 | Done | 2014-03-19
#107 Play against easy difficulty AI | @jamesKostiuk | 2014-02-28 | Done | 2014-03-13
#109 Preparation - Learn Facebook Android API | @goddamnpete | 2014-02-28 | Done | 2014-03-04
#110 Testing - Construct and execute more elaborate testing for possible moves | @goddamnpete | 2014-02-28 | Done | 2014-03-04
#114 Push notifications - Android architecture design | @ChrisKdon | 2014-03-04 | Done | 2014-03-09
#116 Design - create UI flow diagrams | @kubasub | 2014-03-04 | Done | 2014-03-05
#118 Construction - update MainActivity buttons | @kubasub | 2014-03-05 | Done | 2014-03-05
#119 Design - update UI control tables for testing | @kubasub | 2014-03-05 | Done | 2014-03-06
#120 Construction - add functionality to see list of players | @kubasub | 2014-03-05 | Done | 2014-03-07
#121 Construction - create settings screen | @kubasub | 2014-03-05 | Done | 2014-03-09
#122 COPPA Compliance EULA | @benstitt | 2014-03-05 | Done | 2014-03-05
#123 Research - Help Section | @benstitt | 2014-03-05 | Done | 2014-03-06
#124 Push notifications - server architecture design | @ChrisKdon | 2014-03-05 | Done | 2014-03-19
#125 Fix android game state manager | @ChrisKdon | 2014-03-05 | Done | 2014-03-09
#126 Setup server | @ChrisKdon | 2014-03-05 | Done | 2014-03-07
#127 Online game list activity - Architecture design | @ChrisKdon | 2014-03-05 | Done | 2014-03-18
#128 Networking - design android REST interface architecture | @ChrisKdon | 2014-03-05 | Done | 2014-03-09
#129 Server - Design/Create NodeJS/Java Communications | @ChrisKdon | 2014-03-05 | Done | 2014-03-06
#130 UI - Update UI Control elements | @SaajidM | 2014-03-05 | Done | 2014-03-05
#131 Construction - rearchitect and implement dialogs | @kubasub | 2014-03-05 | Done | 2014-03-05
#132 Implement login with Facebook | @goddamnpete | 2014-03-05 | Done | 2014-03-06
#133 Design - online game list activity mock up | @taywhited | 2014-03-06 | Done | 2014-03-07
#134 Design - new online game (and Dialog) mock up | @taywhited | 2014-03-06 | Done | 2014-03-07
#135 Design - list of players mock up | @taywhited | 2014-03-06 | Done | 2014-03-06
#136 Design - settings mock up | @taywhited | 2014-03-06 | Done | 2014-03-07
#139 Networking - create database | @goddamnpete | 2014-03-06 | Done | 2014-03-18
#140 Writing - Help section | @benstitt | 2014-03-06 | Done | 2014-03-11
#141 Testing - create test plan | @SaajidM | 2014-03-07 | Done | 2014-03-18
#142 Design - no connectivity banner mock up | @taywhited | 2014-03-07 | Done | 2014-03-11
#146 Construction - create UI for onlineListActivity | @kubasub | 2014-03-09 | Done | 2014-03-09
#147 Construction - code setting section | @kubasub | 2014-03-09 | Done | 2014-03-09
#148 Construction - create new game dialog | @kubasub | 2014-03-09 | Done | 2014-03-09
#151 Working push notification manager | @ChrisKdon | 2014-03-09 | Done | 2014-03-11
#155 GamePlay - add new win conditions | @SaajidM | 2014-03-11 | Done | 2014-03-12
#157 Animate/sleep AI Move Drawing thread | @ChrisKdon | 2014-03-13 | Done | 2014-03-16
#163 Design - ER diagrams | @taywhited | 2014-03-13 | Done | 2014-03-15
#164 Fix stack overflow issue in game state manager | @kubasub | 2014-03-13 | Done | 2014-03-14
#165 DB - refactor naming conventions | @taywhited | 2014-03-13 | Done | 2014-03-15
#166 Add Help section text to application | @kubasub | 2014-03-13 | Done | 2014-03-16
#175 Testing - manual testing - medium AI | @SaajidM | 2014-03-18 | Done | 2014-03-19
#176 Testing - manual testing - dialogs | @saajidM | 2014-03-18 | Done | 2014-03-18
#177 Testing - automated regression testing | @saajidM | 2014-03-18 | Done | 2014-03-18
#178 Testing - automated testing - UI Unit Test | @saajidM | 2014-03-18 | Done | 2014-03-18
#179 Testing - automated testing - UI Integration | @saajidM | 2014-03-18 | Done | 2014-03-18
#182 Testing - Manual testing - Easy AI Retest 2 | @saajidM | 2014-03-19 | Done | 2014-03-19
#137 Needs connectivity activity | @kubasub |  | push out
#167 Rewrite game rules | @taywhited | 2014-03-15 | Done | 2014-03-19
#171 Testing - ease of use testing | @saajidM | 2014-03-17 | Done | 2014-03-19
#173 Fixing getpossiblemoves() - not leaving goal | @goddamnpete |  | push out
#174 Testing Acceptance Testing | @benstitt | 2014-03-18 | Done | 2014-03-19

## Iteration #3 Burndown
Date | Iteration 2 Total | Iteration 2 Done | Total | Done | To Do | Ideal Done
2014-02-27 | 1 | 0 | 2 | 0 | 2 | 3.3333
2014-02-28 | 7 | 0 | 6 | 0 | 6 | 6.6667
2014-03-03 | 12 | 0 | 6 | 0 | 6 | 10
2014-03-04 | 12 | 0 | 8 | 2 | 6 | 13.3333
2014-03-05 | 12 | 0 | 23 | 8 | 15 | 16.6667
2014-03-06 | 13 | 1 | 29 | 13 | 16 | 20
2014-03-07 | 22 | 1 | 31 | 18 | 13 | 23.3333
2014-03-10 | 23 | 1 | 35 | 25 | 10 | 26.6667
2014-03-11 | 26 | 2 | 36 | 28 | 8 | 30
2014-03-12 | 26 | 2 | 36 | 29 | 7 | 33.3333
2014-03-13 | 27 | 5 | 41 | 30 | 11 | 36.6667
2014-03-14 | 29 | 9 | 41 | 31 | 10 | 40
2014-03-17 | 32 | 14 | 43 | 35 | 8 | 43.3333
2014-03-18 | 32 | 21 | 49 | 43 | 6 | 46.6667
2014-03-19 | 32 | 32 | 50 | 50 | 0 | 50
Formulas:
Date = WORKDAY([Date, row above],1)

## Iteration #4
| Owner | Created | Status | Completed
#117 Construction - rotating the game board for offline play | @kubasub | 2014-03-03 | Cancelled | 2014-03-01
#137 Needs connectivity activity | @kubasub | 2014-03-03 | Done | 2014-03-23
#159 Register player | @ChrisKdon | 2014-03-13 | Done | 2014-03-20
#173 Fixing getPossibleMoves - not leaving goal | @ChrisKdon | 2014-03-19 | Done | 2014-03-25
#184 Medium AI Problem | @JamesKostiuk | 2014-03-20 | Done | 2014-03-28
#191 Database - finish off remaining testing and refactoring | @goddamnpete | 2014-03-21 | Done | 2014-03-29
#194 Construction - modify username | @kubasub | 2014-03-20 | Done | 2014-04-01
#195 Construction - connect online list with the server | @kubasub | 2014-03-20 | Done | 2014-04-02
#198 Resume dialog bug | @kubasub | 2014-03-20 | Done | 2014-03-22
#209 Create test plan | @SaajidM | 2014-04-02 | Done | 2014-04-02
#210 Do Manual Testing | @SaajidM | 2014-04-01 | Done | 2014-04-03
#212 Create Ease of Use Tasks | @SaajidM | 2014-04-01 | Done | 2014-04-02
#106 Play against Hard Difficulty AI | @JamesKostiuk | 2014-03-03 | Done | 2014-04-03
#156 Construction - Notifications Manager | @kubasub | 2014-03-13 | Done | 2014-04-03
#158 Cut AI Code from Android | @BenStitt | 2014-03-13 | Done | 2014-04-03
#189 Construction - Create Server API | @ChrisKdon | 2014-03-20 | Done | 2014-04-03
#190 Construction - Client Side API | @Kubasub | 2014-03-20 | Done | 2014-04-03
#192 Construction - Server side hooking up AI | @ChrisKdon | 2014-03-20 | Done | 2014-04-03
#193 Construction - create client side push message interface | @ChrisKdon | 2014-03-20 | Done | 2014-04-03
#196 Construction - online game activity network calls | @Kubasub | 2014-03-20 | Done | 2014-04-03
#197 Construction - create network player | @ChrisKdon | 2014-03-20 | Done | 2014-04-03
#199 Construction - when players have been inactive replace them with AI | @ChrisKdon | 2014-03-20 | Done | 2014-04-03
#200 Construction - when players have been waiting for more then 1 minute fill the rest of the game with AIs | @ChrisKdon | 2014-03-20 | Done | 2014-04-03
#211 Do regression testing | @Kubasub | 2014-04-01 | Done | 2014-04-03
#213 Do Ease of Use Testing | @curtesmith | 2014-04-01 | Done | 2014-04-03
#214 Create presentation for final iteration | @curtesmith | 2014-04-01 | Done | 2014-04-03

## Iteration #4 Burndown
Date | Iteration 3 Total | Iteration 3 Done | Total | Done | To Do | Ideal Done
2014-03-20 | 2 | 0 | 19 | 2 | 17 | 2.3636
2014-03-21 | 8 | 2 | 20 | 2 | 18 | 4.7273
2014-03-24 | 23 | 8 | 20 | 4 | 16 | 7.0909
2014-03-25 | 29 | 13 | 20 | 5 | 15 | 9.4545
2014-03-26 | 36 | 28 | 20 | 5 | 15 | 11.8182
2014-03-27 | 36 | 29 | 20 | 5 | 15 | 14.1818
2014-03-28 | 41 | 30 | 20 | 6 | 14 | 16.5455
2014-03-31 | 41 | 31 | 20 | 7 | 13 | 18.9091
2014-04-01 | 43 | 35 | 25 | 8 | 17 | 21.2727
2014-04-02 | 49 | 43 | 26 | 11 | 15 | 23.6364
2014-04-03 | 50 | 50 | 26 | 26 | 0 | 26
Formulas:
Date = WORKDAY([Date, row above],1)

## Team schedules
Time | Sun | Mon | Tues | Wed | Thu | Fri | Sat
900 |  |  | James Kuba |  | Peter Taylor
930 |  | James Taylor | James Kuba Peter |  | Kuba Peter Taylor | James Taylor Kuba
1000 |  | James Taylor | James Kuba Peter |  | Kuba Peter Taylor | James Taylor Kuba
1030 |  | James Taylor | James Kuba Peter |  | Kuba Peter Taylor | James Taylor Kuba
1100 |  |  | Kuba |  | Peter Taylor | Kuba
1130 |  |  | Kuba |  | Peter Taylor | Kuba
1200 |  | Taylor | Kuba |  | Kuba | James Kuba
1230 |  | Taylor | James |  | James Kuba | James Kuba
1300 |  | Taylor | James |  | James Kuba | James
1330 |  | Taylor | James |  | James Kuba | James
1400 |  |  |  | Kuba | Kuba | Kuba
1430 |  |  |  | Kuba | Kuba | Kuba
1500 |  |  |  | Kuba | Kuba | Kuba
1530 |  |  |  | Peter Taylor | Kuba | Peter Taylor
1600 |  |  |  | Peter Taylor |  | Peter Taylor
1630 |  |  |  | Peter Taylor |  | Peter Taylor
1700
1730
1800
1830
1900 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
1930 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2000 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2030 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2100 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2130 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2200