## Team Capacity Calculations
Team Capacity Calculations
Release Level Plan |  | Iteration Level Plan
Start | 2014-01-09 | Iteration # | # Weeks | Hours
Finish | 2014-03-27 | 1st iteration | 4 | 192
Last Day of Class | 2014-04-04 | 2nd iteration | 3 | 144
|  | 3rd iteration | 3 | 144
Work Days | 77 | 4th iteration | 1 | 48
Work Weeks | 11
# of People | 8 | Total Hours |  | 528
Hours/Week/Person | 6
Total Hours | 528

## Product Backlog
Feature Set | Description | Order | Target Iteration
Game | create a game | 1 | 1
Game | specify game settings (# of players, player color) | 2 | 1
Game | show hotseat game board | 3 | 1
Game | peg animation | 4 | 2
Game | hotseat (offline, no AI) | 5 | 2
Game | close game | 6 | 2
Account | acheivements
Account | anonymous accounts
Account | create an account
Account | edit/delete account
Account | friends list
Account | game history, rank, etc.
Account | leaderboards/ranking
Account | login with Facebook
Account | logout
Account | message inbox
Account | password reset (via android ... if poss.)
Account | profile page
Admin | admin screen for system analytics
Admin | COPPA compliance
Game | 1st-6th place get points
Game | AI takes over when user forfeit
Game | demo mode (to watch AI)
Game | friend request
Game | game playback
Game | in-game chat
Game | multiple games
Game | pegs left to win
Game | play against an AI
Game | player label
Game | set music/fx volume
Game | timed games
Game | timeless (long) games
Game | toggle show possible moves
Game | turn notification
Help | "help" section
Web | app webpage
game lobby

## Iteration #1
Description | Estimate | Actual | Owner | Created | Status | Completed
Communication - consolidate the requirements and design documentation | 4 |  | @BenStitt | 2014-01-19 | In Progress | 2014-02-05 | binder
Communication - create terms of service document | 2 |  | @BenStitt | 2014-01-19 | Done | 2014-01-29
Construction - create a board and adding pegs | 4 |  | Peter + @ChrisKdon | 2014-01-19 | In Progress | 2014-02-04
Construction - create the first 2 activities, minus the game board | 6 |  | @kubasub | 2014-01-19 | In Progress | 2014-02-04
Construction - finalize the creation of the game board grid | 8 |  | @ChrisKdon | 2014-01-19 | In Progress | 2014-02-04
Construction - UI layout files, not colours | 7 |  | @kubasub | 2014-01-19 | In Progress | 2014-02-04
Design - AI design with 4 to 5 different difficulties/strategies | 7 |  | @JamesKostiuk | 2014-01-19 | In Progress | 2014-02-04
Design - create naming conventions for Testing | 0.5 | 0.5 | @kubasub | 2014-01-19 | Done | 2014-01-20
Design - creating documentation of the creation of the game board grid | 4 |  | Peter | 2014-01-19 | Done | 2014-02-01
Design - creating documentation of the high level architecture | 10 |  | @ChrisKdon | 2014-01-19 | In Progress | 2014-02-04
Design - UI flow | 3 | 3 | @kubasub | 2014-01-19 | Done | 2014-01-20
Design - UI screen mockups with styles | 8 |  | @taywhited | 2014-01-19 | Done | 2014-02-02
Testing - create test plan from UI design | 4 |  | @SaajidM | 2014-01-19 | In Progress | 2014-02-04
Testing - ease of use testing | 2 |  | @SaajidM | 2014-02-01 |  | 2014-02-05
Testing - implement test cases | 8 |  | @SaajidM | 2014-01-23 |  | 2014-02-05
Testing - run the integration and performance tests | 2 |  | @SaajidM | 2014-01-19 |  | 2014-02-05
| 79.5 | 3.5

## Iteration #1 Burndown
Date | Total | Done | To Do
2014-01-19 | 14 | 0 | 14
2014-01-20 | 14 | 2 | 12
2014-01-21 | 14 | 2 | 12
2014-01-22 | 14 | 2 | 12
2014-01-23 | 15 | 2 | 13
2014-01-24 | 15 | 2 | 13
2014-01-27 | 15 | 2 | 13
2014-01-28 | 15 | 2 | 13
2014-01-29 | 15 | 3 | 12
2014-01-30 | 15 | 3 | 12
2014-01-31 | 15 | 3 | 12
2014-02-03 | 16 | 5 | 11
2014-02-04 | 16 | 12 | 4
2014-02-05 | 16 | 16 | 0
Formulas:
Date = WORKDAY([Date, row above],1)

## Team schedules
Time | Sun | Mon | Tues | Wed | Thu | Fri | Sat
900 |  |  | James Kuba |  | Peter Taylor
930 |  | James Taylor | James Kuba Peter |  | Kuba Peter Taylor | James Taylor Kuba
1000 |  | James Taylor | James Kuba Peter |  | Kuba Peter Taylor | James Taylor Kuba
1030 |  | James Taylor | James Kuba Peter |  | Kuba Peter Taylor | James Taylor Kuba
1100 |  |  | Kuba |  | Peter Taylor | Kuba
1130 |  |  | Kuba |  | Peter Taylor | Kuba
1200 |  | Taylor | Kuba |  | Kuba | James Kuba
1230 |  | Taylor | James |  | James Kuba | James Kuba
1300 |  | Taylor | James |  | James Kuba | James
1330 |  | Taylor | James |  | James Kuba | James
1400 |  |  |  | Kuba | Kuba | Kuba
1430 |  |  |  | Kuba | Kuba | Kuba
1500 |  |  |  | Kuba | Kuba | Kuba
1530 |  |  |  | Peter Taylor | Kuba | Peter Taylor
1600 |  |  |  | Peter Taylor |  | Peter Taylor
1630 |  |  |  | Peter Taylor |  | Peter Taylor
1700
1730
1800
1830
1900 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
1930 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2000 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2030 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2100 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2130 |  | James Kuba Taylor | James Kuba Taylor Peter |  | James Kuba Taylor Peter
2200

## To Do List
Task | Assigned To | Date Created
Research continous integration options | Curtis | 2014-01-09
Build some project reporting template options | Curtis | 2014-01-09
Android Testing Frameworks | Sajid | 2014-01-09
Create some sample testing documentation templates (test plan, test cases) | Sajid | 2014-01-09
Build ER Models for the database | Peter | 2014-01-09
create some sample Use Case documentation Templates | Ben | 2014-01-09
Managing our To Do List | Ben | 2014-01-09
Animation, Canvas | Taylor | 2014-01-09
Start specing out architecture models and template | Chris | 2014-01-09
UI Design and screen mock ups | Kuba | 2014-01-09
Research AI options (minimax) | James | 2014-01-09
Talk with Prof. W. about scheduling regular meetings | Curtis | 2014-01-09
Talk with Prof. W. about making the GitHub repo public | Curtis | 2014-01-09