## Slide 1
Prepared by Logical Operators
for COSC 3F00
February 6th, 2014

## Slide 2
Team Introductions

## Slide 3: Using Agile Principles
Our highest priority is to satisfy the customer through early and continuous delivery of valuable software
Working software is the primary measure of progress
At regular intervals the team reflects on how to become more effective then tunes and adjusts its behavior accordingly

## Slide 4: Communication
reviewed the rules and game play of chinese checkers
brainstormed and built a list of 38 high level use cases

## Slide 5
Feature Set | Description | Order | Target Iteration
Game | create a game | 1 | 1
Game | specify game settings (# of players, player color) | 2 | 1
Game | show hotseat game board | 3 | 1
Game | peg animation | 4 | 2
Game | hotseat (offline, no AI) | 5 | 2
Game | close game | 6 | 2
Account | acheivements |  | 
Account | anonymous accounts |  | 
Account | create an account |  | 
Account | edit/delete account |  | 

## Slide 6
Feature Set | Description | Order | Target Iteration
Account | friends list |  | 
Account | game history, rank, etc. |  | 
Account | leaderboards/ranking |  | 
Account | login with Facebook |  | 
Account | logout |  | 
Account | message inbox |  | 
Account | password reset (via android ... if poss.) |  | 
Account | profile page |  | 
Admin | admin screen for system analytics |  | 
Admin | EULA + COPPA compliance |  | 

## Slide 7
Feature Set | Description | Order | Target Iteration
Game | 1st-6th place get points |  | 
Game | AI takes over when user forfeit |  | 
Game | demo mode (to watch AI) |  | 
Game | friend request |  | 
Game | game playback |  | 
Game | in-game chat |  | 
Game | multiple games |  | 
Game | pegs left to win |  | 
Game | play against an AI |  | 
Game | player label |  | 
Game | set music/fx volume |  | 

## Slide 8
Feature Set | Description | Order | Target Iteration
Game | timed games |  | 
Game | timeless (long) games |  | 
Game | toggle show possible moves |  | 
Game | turn notification |  | 
Help | "help" section |  | 
Web | app webpage |  | 
 | game lobby |  | 

## Slide 9: Planning
Calculated 528 total budgeted hours
Split budget into time-boxed iterations
Prioritized the list of use cases
Pulled highest priority use cases into first iteration
Decided on tools to use

## Slide 10
Team Capacity Calculations
Release Level Plan |  | Iteration Level Plan
Start | 9-Jan |  | Iteration # | # Weeks | Hours
Finish | 27-Mar |  | 1st iteration | 4 | 192
Last Day of Class | 4-Apr |  | 2nd iteration | 3 | 144
 |  |  | 3rd iteration | 3 | 144
Work Days | 77 |  | 4th iteration | 1 | 48
Work Weeks | 11 |  |  |  | 
# of People | 8 |  | Total Hours | 528
Hours/Week/Person | 6 |  |  |  | 
Total Hours | 528 |  |  |  | 

## Slide 11: Project Timeline

## Slide 12: Tools
Google Drive
GitHub (https://github.com/kubasub/chinese-checkers)
Android Studio (http://developer.android.com/sdk/installing/studio.html)
SourceTree (http://www.sourcetreeapp.com)

## Slide 13: More Tools
Paint.NET
Corel PaintShop Photo Pro X3
Adobe Photoshop CS5.1
Pen and paper

## Slide 15: Design
Use Cases
User Interface mockups
Data Flow and UML
Test plan

## Slide 18: Construction
code and unit test
integration test
performance test
stress test
usability test
acceptance test

## Slide 19
Demonstration

## Slide 20
Feedback?
Q&A

## Slide 21
Thank you